## Gantt
AI-Powered Autonomous Vacuum Cleaner Robot - Project Gantt Chart (Daily View)
Project start | 2026-08-28 |  | Projected
Project end | 2026-12-02 |  | Actual | [5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14
[9 empty] | Aug |  | September 2026 | [21 empty] | October 2026 | [21 empty] | November 2026 | [20 empty] | Dec
 | time axis 2026-08-28 to 2026-12-02
Phase | Task | Week(s) | Type | Start | Finish | Work Days | Status | Notes / Parallel Task | time axis 2026-08-28 to 2026-12-02
1. Design & Planning | Finalise system architecture & confirm component selection | Weeks 1-2 | Projected | 2026-08-28 | 2026-09-10 | 10 | Done
|  |  | Actual | 2026-08-28 | 2026-09-10 | 10
1. Design & Planning | Order components (Cytron / Shopee) | Weeks 1-3 | Projected | 2026-08-28 | 2026-09-16 | 14 | In progress
|  |  | Actual | 2026-09-01
1. Design & Planning | Design 3D print files (chassis body, top cover, sensor mounts, impeller housing) | Weeks 1-5 | Projected | 2026-09-01 | 2026-09-25 | 19 | In progress | Parallel with component delivery
Actual
1. Design & Planning | Draft hardware & software system block diagrams + 3D concept sketch | Weeks 1-3 | Projected | 2026-08-31 | 2026-09-11 | 10 | Done
|  |  | Actual | 2026-09-01 | 2026-10-09 | 29
1. Design & Planning | Design dustbin (3D print file) | Weeks 3-5 | Projected | 2026-09-14 | 2026-09-25 | 10 | In progress | Added
Actual
1. Design & Planning | Review & finalise design documentation | Weeks 3-5 | Projected | 2026-09-14 | 2026-09-28 | 11 | In progress | Logbooks 1-4
|  |  | Actual | 2026-09-14
2. Hardware Build | 3D print chassis parts (body, top cover, wheel mounts) | Weeks 5-7 | Projected | 2026-09-29 | 2026-10-09 | 9 | In progress | Printing using Bambu
|  |  | Actual | 2026-10-01
2. Hardware Build | Assemble chassis frame (base) | Weeks 6-8 | Projected | 2026-10-07 | 2026-10-16 | 8 | In progress | CRITICAL - base must be complete; parallel with printing
|  |  | Actual | 2026-10-04
2. Hardware Build | Wire drivetrain motors + encoders | Weeks 7-8 | Projected | 2026-10-12 | 2026-10-16 | 5 | In progress
|  |  | Actual | 2026-10-09
2. Hardware Build | Wire power distribution (3S LiPo, switch / fuse, 5V buck converter) | Week 7 | Projected | 2026-10-12 | 2026-10-14 | 3 |  | Power for RPi 5, Arduino, motors, blower
Actual
2. Hardware Build | Bench-test power rails & battery protection | Weeks 7-8 | Projected | 2026-10-15 | 2026-10-16 | 2 |  | Check 11.1V and 5V before connecting electronics
Actual
2. Hardware Build | Wire sensors (FC-51 IR sensor, dust sensor, IR docking beacon) | Weeks 7-8 | Projected | 2026-10-12 | 2026-10-16 | 5 |  | Follow GPIO wiring diagram
Actual
2. Hardware Build | Wire compute & peripherals (RPi 5, Arduino, RPLIDAR, Pi camera) | Weeks 7-8 | Projected | 2026-10-14 | 2026-10-19 | 4 |  | Final wiring check & cable tidy
Actual
2. Hardware Build | Bench-test motors & motor drivers | Weeks 7-8 | Projected | 2026-10-12 | 2026-10-16 | 5
Actual
2. Hardware Build | 3D print dustbin | Weeks 7-8 | Projected | 2026-10-12 | 2026-10-16 | 5 |  | Added - after chassis print
Actual
2. Hardware Build | 3D print impeller housing & brush roller mounts | Weeks 6-8 | Projected | 2026-10-05 | 2026-10-16 | 10 |  | Parallel with drivetrain wiring
Actual
2. Hardware Build | Assemble impeller + suction blower + brush motor | Weeks 7-9 | Projected | 2026-10-12 | 2026-10-23 | 10
Actual
2. Hardware Build | Integrate suction assembly into chassis | Weeks 8-9 | Projected | 2026-10-19 | 2026-10-23 | 5
Actual
2. Hardware Build | Bench-test suction system | Weeks 8-9 | Projected | 2026-10-19 | 2026-10-23 | 5 | In progress
|  |  | Actual | 2026-10-06
3. Software & AI | lidar.py | Weeks 5-7 | Projected | 2026-09-28 | 2026-10-09 | 10 |  | Parallel with suction build
Actual
3. Software & AI | motor.py | Weeks 7-8 | Projected | 2026-10-12 | 2026-10-16 | 5
Actual
3. Software & AI | sensors.py (IR + dust sensor) | Weeks 7-8 | Projected | 2026-10-12 | 2026-10-16 | 5
Actual
3. Software & AI | odometry.py | Weeks 7-8 | Projected | 2026-10-12 | 2026-10-16 | 5
Actual
3. Software & AI | Integration test of hardware modules | Weeks 8-9 | Projected | 2026-10-19 | 2026-10-23 | 5
Actual
3. Software & AI | SLAM.py (LiDAR mapping) | Weeks 7-9 | Projected | 2026-10-12 | 2026-10-23 | 10 |  | CRITICAL - navigation depends on the map
Actual
3. Software & AI | path_planner.py | Weeks 8-10 | Projected | 2026-10-19 | 2026-10-30 | 10
Actual
3. Software & AI | controller.py | Weeks 8-10 | Projected | 2026-10-19 | 2026-10-30 | 10
Actual
3. Software & AI | SLAM + control integration test | Weeks 9-10 | Projected | 2026-10-26 | 2026-10-30 | 5
Actual
3. Software & AI | Collect floor / dirt training images | Weeks 4-6 | Projected | 2026-09-21 | 2026-10-02 | 10 |  | Parallel with SLAM work
Actual
3. Software & AI | Train surface_classifier.py | Weeks 5-8 | Projected | 2026-09-28 | 2026-10-16 | 15 |  | Model training started
Actual
3. Software & AI | Train dirt_detector.py | Weeks 6-8 | Projected | 2026-10-05 | 2026-10-16 | 10
Actual
3. Software & AI | Convert & test TFLite models on RPi 5 | Weeks 8-9 | Projected | 2026-10-19 | 2026-10-23 | 5
Actual
4. Integration & Testing | Integrate classifier output with suction control logic | Weeks 9-11 | Projected | 2026-10-26 | 2026-11-06 | 10
Actual
4. Integration & Testing | Obstacle avoidance testing | Weeks 9-10 | Projected | 2026-10-25 | 2026-11-01 | 5
Actual
4. Integration & Testing | Bug fixing & refinement | Week 10 | Projected | 2026-10-30 | 2026-11-05 | 5
Actual
4. Integration & Testing | Build Flask REST API (server.py) | Weeks 9-11 | Projected | 2026-10-25 | 2026-11-08 | 10 |  | Parallel with cleaning logic
Actual
4. Integration & Testing | Set up MQTT broker & client (Mosquitto) | Weeks 9-10 | Projected | 2026-10-26 | 2026-11-05 | 9
Actual
4. Integration & Testing | Develop Flutter visualiser app | Weeks 9-12 | Projected | 2026-10-26 | 2026-11-15 | 15
Actual
4. Integration & Testing | Full-system integration (robot + app) | Weeks 10-12 | Projected | 2026-11-01 | 2026-11-13 | 10
Actual
4. Integration & Testing | End-to-end system testing | Weeks 11-12 | Projected | 2026-11-09 | 2026-11-17 | 7
Actual
4. Integration & Testing | Debugging | Weeks 12-13 | Projected | 2026-11-16 | 2026-11-20 | 5
Actual
4. Integration & Testing | Safety / regulatory checks | Weeks 12-13 | Projected | 2026-11-16 | 2026-11-20 | 5
Actual
5. Report & Project Defence | Report writing - draft chapters (intro, design, implementation) | Weeks 8-12 | Projected | 2026-10-19 | 2026-11-13 | 20 |  | Start drafting while building
Actual
5. Report & Project Defence | Report writing - testing, results & conclusion | Weeks 12-13 | Projected | 2026-11-16 | 2026-11-20 | 5 |  | After testing wraps up
Actual
5. Report & Project Defence | Compile appendices, logbooks & IEEE references | Weeks 12-13 | Projected | 2026-11-16 | 2026-11-20 | 5
Actual
5. Report & Project Defence | Submit final project report | Week 13 | Projected | 2026-11-25 | 2026-11-25 | 1 |  | DEADLINE - Wed 25 Nov
Actual
5. Report & Project Defence | Viva preparation - presentation slides | Weeks 12-14 | Projected | 2026-11-15 | 2026-11-27 | 10 |  | Parallel with report review
Actual
5. Report & Project Defence | Submit viva slides | Week 14 | Projected | 2026-11-30 | 2026-11-30 | 1 |  | DEADLINE - Mon 30 Nov
Actual
5. Report & Project Defence | Viva preparation - demo setup & robot readiness check | Weeks 13-14 | Projected | 2026-11-23 | 2026-12-01 | 7
Actual
5. Report & Project Defence | Viva preparation - mock viva & Q&A rehearsal | Week 14 | Projected | 2026-11-27 | 2026-12-01 | 3
Actual
5. Report & Project Defence | Project defence (viva) | Week 14 | Projected | 2026-12-02 | 2026-12-02 | 1 |  | DEADLINE - Wed 2 Dec
Actual